## Sheet1
Section: | Task: |  | Date: |  | Duration (Hours): | Comments:
Setup Tasks | 1.1 | Project outline submission | 2019-10-11 | 2019-10-18
| 1.2 | Initial project meeting | 2019-11-12 | 2019-11-12
Planning and Documentation | 2.1 | Reference/resource gathering | 2019-11-12 | 2019-12-05 | 10 | Send Joe 4 high quality sources before 5th
| 2.2 | Reference/resource analysis | 2019-12-05 | 2020-01-20 | 15 | Read sources/annotate and mark important quotes
| 2.3 | Reference/resource review | 2020-10-22 | 2020-02-14 | 5 | Summarise sources in table
| 2.4 | System Requirements Specification Document | 2020-02-02 | 2020-02-10 | 10 | Complete in IEEE Style
| 2.5 | Participant Gathering | 2020-02-03 | 2020-02-10 | 30 | Must find >10 participants
| 2.6 | Work Breakdown Structure Document | 2020-02-10 | 2020-02-11 | 15 | Use SRS tasks, create project outline and milestones
| 2.7 | Develop questionnaire 1 | 2020-02-11 | 2020-02-13 | 15 | Must investigate topics from AE1
| 2.8 | Create user manual/install documentation | 2020-02-14 | 2020-02-16 | 10 | Must direct users on download/installation process
| 2.9 | Create user manual/feature explanation section | 2020-02-18 | 2020-02-20 | 10 | Must direct users on configuring/setup process
Initial Implementation | 3.1 | Core functionality development | 2020-02-21 | 2020-03-08 | 80 | Must implement most core features
| 3.2 | Initial software testing | 2020-03-08 | 2020-03-10 | 20 | Use software to find bugs
| 3.3 | Distribute project and documentation | 2020-03-11 | 2020-03-11 | 5 | Send packages out to testers
Software Trial 1 | 4.1 | Software trial phase 1 | 2020-03-11 | 2020-03-18 | 20 | Directed all users on how to use software, continue to answer questions
| 4.2 | Suggestions/improvements gathering | 2020-03-18 | 2020-03-19 | 10 | Directly message all users to gain additional feedback, use "comments" section on forms
| 4.3 | Trial 1 feedback processing | 2020-03-21 | 2020-03-22 | 10 | Compile all information, checklist fixes to be made
| 4.4 | Software fixes | 2020-03-22 | 2020-03-24 | 10 | Fix all software bugs and problems identified
| 4.5 | Additional feature planning | 2020-03-25 | 2020-03-26 | 10 | Plan features based on feedback
| 4.6 | Additional features/fixes implementation | 2020-03-27 | 2020-03-29 | 25 | All planned additional features should be implemented
| 4.7 | Software testing | 2020-03-30 | 2020-03-31 | 20 | Test software again to find additional bugs, verify fixes have eliminated old bugs
| 4.8 | User manual/documentation update | 2020-04-01 | 2020-04-03 | 5 | Update documents after changes
Software Trial 2 | 5.1 | Develop questionnaire 2 | 2020-04-04 | 2020-04-08 | 10 | Add new section on direct comparisons to firewall-style blockers
| 5.2 | Distribute updated project and documentation | 2020-04-08 | 2020-04-08 | 5 | Send packages out to participants
| 5.3 | Software trial phase 2 | 2020-04-08 | 2020-04-15 | 20 | Direct all users on new software, answer all questions throughout, monitor progress
| 5.4 | Suggestions/improvements gathering | 2020-04-15 | 2020-04-17 | 10 | Gather all feedback from emails, message testers to gather additional changes
| 5.5 | Trial 2 feedback processing | 2020-04-17 | 2020-04-18 | 10 | Plan fixes based on user feedback
| 5.6 | Software Fixes | 2020-04-28 | 2020-04-21 | 10 | All planned fixes must be made
| 5.7 | Additional feature planning | 2020-04-21 | 2020-04-21 | 10 | Plan new set of features from feedback
| 5.8 | Additional features/fixes implementation | 2020-04-22 | 2020-04-23 | 30 | Make new changes, test and fix newest code
| 5.9 | Software testing | 2020-04-24 | 2020-04-26 | 20 | Test software to find all remaining bugs from implementation
| 5.1 | User manual/documentation update | 2020-04-27 | 2020-04-29 | 5 | Update all documents to reflect newest state of the software
| 5.11 | Distribute updated project and documentation | 2020-04-29 | 2020-04-29 | 5 | Send out trial 3 packages to all testers
Software Trial 3 | 6.1 | Software trial phase 3 | 2020-04-29 | 2020-05-06 | 20 | Manage tests and respond to all feedback for the week
| 6.2 | Suggestions/improvements gathering | 2020-05-07 | 2020-05-10 | 10 | Compile all information on additional fixes and changes from test
| 6.3 | Trial 3 feedback processing | 2020-05-11 | 2020-05-12 | 10 | Enter all feedback results into results document
| 6.4 | Data analysis/conclusions | 2020-05-13 | 2020-05-20 | 20 | Create new file to alalyse results from all tests, make conclusions
Total: |  |  |  |  | 530